## Slide 1
Agency Priority Goal Action Plan
Goal Leader: Mona Siddiqui, Office of the Chief Technology Officer (CTO)
Combined Data Analyses
Fiscal Year 2019, Quarter 2

## Slide 2
Overview
Goal Statement
  Increase combined analysis of disparate datasets in order to achieve better insights. By September 30, 2019 HHS will develop and implement an enterprise wide data governance model. This will enable more efficient and effective processes for sharing inter-agency data beyond a dataset’s primary purpose. Two use cases of inter-agency data sharing through this process will be tested.
Challenges
  Siloes - HHS has rich data assets that are collected and maintained by separate agencies within the Department. In many instances, Operating Divisions may have specific authorities or mandates to collect data, which makes joint collection or integration of data collection activities difficult.
  Statistical agencies and units must adhere to legal provisions (e.g., Confidential Information Protection and Statistical Efficiency Act) that can inhibit data sharing. HHS programs and services can also be restricted from sharing data by legal provisions. For example, the National Directory of New Hires is a valuable data asset, but it contains the highest degrees of protection.
  CMS, IHS and other Health Insurance Portability and Accountability Act covered entities must adhere to HIPAA regulations for the disclosure and use of covered health information
  Agencies within HHS each serve specific missions and developed systems over time to address their unique needs. However, reexamining the underlying infrastructure can help identify gaps, areas for improvement, and efficiencies. Specifically, HHS needs to develop and implement an enterprise wide data governance strategy.

## Slide 3
Overview
Opportunity
  Multi-sector issues—when an issue touches more than one agency or crosses into multi-disciplines than joint research and analyses occur and benefit everyone involved.
  Technology—advances in computing and IT infrastructure allow for secure sharing of information and enable collaborative work.
  Methodology—advances in statistics, machine learning, data mining, and geographic analysis enable disparate datasets to be combined to reveal new insights and find patterns.

## Slide 4
Leadership
Core Team
  APG Goal Leader: Mona Siddiqui, Chief Data Officer, Office of the CTO, IOS
  Reimagine HHS: Leveraging the Power of HHS Data Core Team

## Slide 5
Goal Structure & Strategies
HHS agencies have experience conducting combined analyses and linking datasets together (both internal and external). However, these are often treated as “one-offs”, experimental, or exploratory rather than a tool to support the overall mission. Encouraging agency collaboration to conduct this work will require providing tools, devoting staff time, and establishing a framework that benefits all involved.
An HHS wide data governance plan will establish ownership and rules for data assets and improve data quality and uniformity.
A streamlined data use agreement infrastructure will enable more seamless interagency data sharing.
Developing an infrastructure that allows for secure and simple sharing of data assets will enable agencies and staff to collaborate on issues that affect multiple agencies such as the opioid epidemic.
Comparing commonly used data architectures and data management tools to open source software and file formats could reveal more efficient ways to analyze and manipulate data assets. Adopting and using flexible open source solutions would also increase the Department’s ability to partner with the private sector.

## Slide 6
Summary of Progress – FY 2019 Q1/Q2
The Goal Team is working to revise the Future State report based on Departmental feedback in an effort to better align with the Evidence Based Act and is progressing through the Department clearance process.
  This report outlines both a potential data governance framework for the Department and identifies important elements that should be included in developing any technical solution to data sharing.
  The report is based on both the feedback gathered in Phase II of this work in conversations with staff across multiple HHS agencies and in a survey of practices both in the public and private sectors.
  OMB approved and apportioned funding for Phase III.
The Goal Team will complete an initial market analysis and expects to acquire the expertise necessary to implement similar efforts in complex health care organizations and at the state level (e.g., Performance Management Hub in Indiana) in May.
The Goal Team began developing a work plan to partner with a National Technical Information Service vehicle through the Commerce Department.
  The Goal Team anticipates launching the prototype platform to enable data sharing and work flow facilitation in two to three months.

## Slide 7
Key Milestones
Milestone Summary |  |  | 
Key Milestone | Milestone Due Date* | Milestone Status | Comments
Develop framework for Department-wide Data Governance Plan | Q4, FY 2018 | Complete | The framework for the Department-wide Data Governance Plan was completed by the end of October.
Deploy two pilots to test the process and infrastructure | Q1, FY 2019 | Ongoing | The Goal Team has been awaiting funding approval and apportionment by OMB. Deployment began in Q3.
Implement Enterprise wide data governance model | Q1, FY 2019 | Ongoing | The Deputy Secretary was briefed on the report and governance model. Implementation to begin in the next month.
Development of Department-wide Data Use Agreements (DUAs) | Q4, FY 2019 | On track | The Goal Team is working with partners across HHS, including the HHS Data Council, to identify elements to include in DUAs.
*Previous Action Plan documentation described expected APG milestone progress to be completed during quarters of the Calendar Year,
rather than the Fiscal Year. For the Q4 update, the Key Milestones Table has been converted to reflect APG progress during quarters of the
Fiscal Year.