## Slide 1
Agency Priority Goal Action Plan
Goal Leader(s):
Dr. Sarah Tomlinson, Associate Deputy Administrator, Veterinary Services (VS) Strategy and Policy
Animal Disease Reduction
June, 2020

## Slide 2
Overview
Goal Statement
To effectively control the spread of animal diseases, USDA supports animal health professionals and other agency partners who use identification technology to quickly trace potentially diseased animals. By September 30, 2021, at least 55 percent of all USDA approved identification tags distributed for cattle will be electronic Radio Frequency Identification (RFID) tags.

## Slide 3
Overview (continued)
Challenges
The transition from metal/visual animal ID tags to RFID technology represents an adjustment for the industry and individual producers. There are approximately 100 million head of cattle in U.S. production at any given time. Transitioning a portion of these animals to a new form of animal ID will require significant engagement with stakeholders.
RFID technology will require improvements to existing databases that track animal health certificate and animal identification data.
The transition from metal/visual animal ID tags to RFID technology also requires the distribution of electronic tag readers to capture RFID tags in more locations.

## Slide 4
Overview (continued)
Opportunity
The current system used to trace animals across State lines is cumbersome, as it requires time to collect data regarding origin and destination through paper documentation. The increased use of RFID technology will allow animal health officials to trace these exposed animals in hours as opposed to days.
RFID technology allows animal health officials to quickly and accurately trace a diseased animal’s location, and reduces unnecessary quarantining and testing of unaffected animals. This minimizes the burden for producers with disease-free animals and helps to protect the financial stability of the industry.
RFID technology will also help permitted animal movements proceed more quickly following a disease outbreak, while ensuring other producers do not receive exposed animals.
RFID technology will require a modernized IT infrastructure to support electronic data. This modernized infrastructure will allow animal health officials to electronically capture and send animal movement data to and from multiple sources.

## Slide 5
Overview (continued)
Opportunity
Now the USDA is looking to further improve the time and accuracy to locate diseased animals by incorporating the use of RFID technology. At the beginning of FY 2020, 40% of official cattle ear tags distributed were equipped with RFID. The next step is to increase the number of USDA approved RFID equipped tags distributed for cattle to 55%. This progress will improve a State’s ability to locate official animal identification numbers, minimizing the impact of a potential animal disease outbreak.

## Slide 6
Leadership & Implementation Team
Oversight and Project Management Team
Veterinary Services (VS)
Executive leadership on Veterinary Services policy and programs
Senior Lead:
Dr. Sarah Tomlinson
VS Strategy & Policy
Develops and coordinates policymaking for Veterinary Services
Senior Lead:
Dr. Aaron Scott
Team Leads:
Dr. Alex Turner
Dr. Sunny Geiser-Novotny
Dr. Alex Reed
Dr. Debbi Donch
Policy & Program Development
Coordinates performance measure reporting for the Agency
Senior Lead:
Eric Hoffman
Team Leads:
Allison Boehm
Shaun Luber

## Slide 7
Structure & Strategies |  | 
Strategy | Outreach Activities (Stakeholder awareness, education, communication, information sharing, etc.) | Technology Improvements (Tags, Equipment, and Databases)
 | Work with producers and industry to identify ways to protect their livelihood. | Modernize IT infrastructure to facilitate use of RFID tags, and sharing of data electronically.
Current state | Engagement with cattle industry representatives, veterinarians, livestock markets, and State Animal Health Officials. | IT infrastructure is under development.
Targeted state | Creation of outreach and educational materials and activities to further acceptable implementation strategies and use of RFID technology. | Modernized Mobile Information Messaging System (MIMS). MIMS is a USDA application used to collect and manage data associated with livestock disease management. Use of Animal Health Events Repository (AHER) to efficiently share data.
Objectives | Better understand producer needs and useful actions. Seek input through States, industry working groups, and producer listening sessions. | Continue MIMS Modernization. Continue to share data with States, Tribes, and 3rd party databases.
Milestone/Metrics | Attend cattle industry association meetings. Attend meetings with State officials. Develop outreach materials for stakeholders. Develop training module(s). Work with State and Industry stakeholders to explore implementation strategies. | Completion of MIMS modernization. Continue to solicit States and 3rd party databases to share data with AHER. Continue to work with industry stakeholders (i.e. slaughter houses and livestock markets) to utilize electronic ID technology.
Goal Structure & Strategies

## Slide 8
Milestone Summary |  |  | 
Key Milestones | Milestone Due Date | Milestone Status | Comments / Change from last quarter
Outreach activities (Supporting measure) |  |  | 
Attend national cattle industry association and State level meetings | FY 20 Q2 FY 21 Q2 | Ongoing | FY20 Q2: Attended approximately 15 meetings with State agencies and Industry organizations, including the National Cattlemen’s Beef Association. These meetings are an opportunity for the Agency to share current information with key stakeholders.
Attend local meetings with stakeholders | FY 20 Q4 FY 21 Q4 | Ongoing | FY20 Q2: Attended approximately 75 meetings, reaching approximately 3,760 stakeholders. Mid-late March meetings cancelled by stakeholders due to COVID-19.
Continue developing outreach materials for stakeholders | Quarterly FY 20, FY 21 | Ongoing | Drafted a series of one-page informational flyers focusing on topics such as Animal Disease Traceability, Premises ID, and use of RFID.
Continue developing training materials for USDA officials and Accredited veterinarians. | Quarterly FY 20, FY 21 | Ongoing | Drafting a series of one-page informational flyers focused on the correct preparation of international health certificates and addressing common errors. These flyers will be delivered to accredited veterinarians.
Work with State and Industry stakeholders to explore implementation strategies | FY 21 Q1 | Ongoing | As of January 31st, 2020, USDA began offering free RFID tags for use on cattle and bison and is working with States on equitable tag distribution.
Key Milestones

## Slide 9
Milestone Summary |  |  | 
Key Milestones | Milestone Due Date | Milestone Status | Comments / Change from last quarter
Technology Improvements (Supporting measure) |  |  | 
Complete Mobile Information Messaging System (MIMS) modernization | FY 21 Q3 | Ongoing | 
Continue to solicit States and 3rd party databases sharing data with the Animal Health Events Repository (AHER) | Quarterly FY 20, FY 21 | Ongoing | USDA provided a webinar demonstration on AHER to State Animal Health Officials and developed an AHER rollout plan.
Continue to work with industry stakeholders (i.e. slaughter facilities and livestock markets) to utilize electronic ID technology | Quarterly FY 20, FY 21 | Ongoing | Continued evaluation, reassessment, and adjustments to feasibility of use of electronic readers in slaughter facilities.
Key Milestones

## Slide 10
Key Indicators
Chart: Percentage of Tags Distributed for Cattle
| FY 2019 Baseline | Q1 FY20 | Q2 FY20 | Q3 FY20 | Q4 FY20 | Q1 FY21 | Q2 FY21 | Q3 FY21 | Q4 FY21
RFID Tags | 0.41009 | 0.45 | 0.45
Metal/Visual Tags | 0.58991 | 0.55 | 0.55
Goal Target

## Slide 11
Summary of Progress – FY20 Q1-Q2
In Q1 and Q2, a total of 7,237,385 USDA approved identification tags for cattle were distributed. Currently, 45% of USDA approved tags being distributed are electronic RFID tags and 55% of USDA approved tags being distributed are visual/metal tags.
In Quarter 2, USDA APHIS Veterinary Services Field Staff provided outreach and education at approximately 75 meetings, reaching approximately 3,760 stakeholders nationwide. These meetings allow the Agency to communicate current information about the Animal Disease Traceability program with key stakeholder groups and share experiences on the value of utilizing electronic RFID tags.
Stakeholders included Tribal ranchers, 4-H participants, organic farmers, accredited veterinarians, veterinary students, and State animal health staff. Meetings scheduled in mid to late March were cancelled by stakeholders due to COVID-19 social distancing needs.
As of January 31st, 2020, USDA began offering free RFID tags to States and accredited veterinarians as an alternative to metal tags for use on cattle and bison. USDA began working with the States on equitable distribution of these tags in mid-Quarter 2.

## Slide 12
Data Accuracy and Reliability
Description/definition of the data: Official animal identification devices provide essential information to achieve timely traceability in response to an animal disease event. The Animal Identification Number (AIN) is an official number that is imprinted on visual official eartags or encoded in electronic identification devices also known as radio frequency identification (RFID). Animal identification number devices may only be manufactured by authorized device manufacturers.
Authorized AIN device manufacturers distribute devices through authorized device managers, documenting this distribution in the Animal Identification Management System (AIMS). AIMS is the Web-based information system used to administer official AINs devices and other animal disease events associated with AINs. The AIN manager maintains records for tracking the distribution of the AINs devices, making this information available when needed for animal disease traces. Databases used for these records include AIMS, State-specific databases, or third-party databases.
Source of data: Data on the distribution of AINs devices from manufacturers to stakeholders are pulled from the AIMS database. These data include AIN devices distributed to retailers, State animal health officials, accredited veterinarians, and producers.
Reliability and accuracy: The AIMS database is dependent on the data entry performed by AIN device managers. The definition and administration of official identification devices are defined in 9 CFR part 86 - Animal Disease Traceability and the Animal Disease Traceability (ADT) General Standards document.
Limitations: It is important to note that data reported from the AIMS database represents devices distributed which does not necessarily equate to devices applied to animals.

## Slide 13
Additional Information
Contributing Programs
Organizations:
State and Federal Animal Health Officials
Tribal Nations
Industry Stakeholders
Program Activities:
Encourage the use of RFID devices through stakeholder outreach and education as well as the distribution of free tags to States.
USDA approved official identification tags are distributed through the USDA Veterinary Services warehouse and private sales direct from the manufacturer.
Provide cooperative agreement funds to States to help them establish and maintain support for State ADT activities. USDA developed national baseline data for tracing exercises administered to States. These tracing exercises document a State’s ability to properly administer, record, and retrieve documents pertaining to official livestock identification and interstate movement.
President’s Management Agenda:
Cross-Agency Priority Goal 1: Modernize IT to Increase Productivity and Security– Develop effective governance organizations and a suite of tools and applications available across agencies that serve the needs of diverse users and facilitate data integration, exchange, and use.
  The use of electronic identification tags for cattle allows for a more efficient transmission of data between State and Federal systems.
Enhancements to the existing databases to increase the ease of collecting data in a standardized format and subsequently providing access to accurate data in real-time, greatly enhances the effectiveness of U.S. traceability and disease control programs.
Private Accredited Veterinarians
Universities and Extension

## Slide 14
Additional Information (continued)
Contributing Programs
Regulations:
9 CFR, part 86: “Traceability for Livestock Moving Interstate” - establishes requirements for the official identification of livestock and documentation for certain interstate movements of livestock. Official identification and movement documentation is essential to tracing livestock when disease is found.
Stakeholder / Congressional Consultations:
It was essential for industry stakeholders from all sectors of the cattle industry to offer their opinions on relevant issues including those related to electronic identification tags for animals. APHIS conducted nine public meetings focused on animal disease traceability as part of outreach efforts in 2017.
The purpose of these meetings was to solicit industry input regarding their experiences with animal disease traceability, and what concerns they had with transitioning to RFID tags.
Many animal health officials, as well as industry stakeholders, acknowledge that the level of traceability necessary in the United States is unachievable with visual only tags.
USDA will continue to work with our state partners and industry to establish appropriate benchmarks to meet to show progress. USDA will also ensure all new traceability cooperative agreements will be contingent on measurable advancements toward its overarching traceability goals.